## HCP Solution on Private Cloud
Activities | Owner | Phase
Infrastructure Setup
Identification of a Co-Lo partner to host the solution | DI | Proposal
Estimate the network connectivity required between Disney Data Center and Co-lo Partner | DI | Proposal
Establish required connectivity between Disney Data Center and Co-Lo Partner | DI | Execution
Identification of compatible tape libraries provider | DI | Proposal
Sizing of the tape libraries required to read tape data | DI | Proposal
Sizing of the physical space required to store physical tapes | DI | Proposal
Sizing of server / storage required to host the solution during migration process
Sizing of server / storage required to host the primary HCP / HCI based solution | DI | Proposal
Sizing of server / storage required to implement DR / Business Continuity and Asset Preservation solutions | DI | Proposal
Sizing of custom archiving, data mover and MAM software in the Data Center and associated integration | DS | Proposal
Acquisition and provisioning of required hardware gear in Data Center | DI | Execution
Professional Services
Identification of a 3rd party to support implementation of HCP / HCI based solution (Audax, Media Translation etc) | DI | Proposal
Installation and configuration of HCP / HCI based solution | DI | Execution
Implementation of HCI workflows and business rules to enrich metadata of existing media assets | 3rd Party / DI | Proposal
Extraction of Data from tape libraries using custom archiving software | 3rd Party/DI | Proposal
Conversion of existing legacy media file formats to newer formats with metadata enrichment | 3rd Party / DI | Proposal
Migration of files to HCP object storage (test environment) | 3rd Party / DI | Proposal
Enrichment of MAM Media Catalogue with additional metadata elements & location of the media asset (during migration) | DS | Proposal
Enhancements of MAM API to support co-existence of media files on-prem and HCP & support additional search criterion | DS | Proposal
Enhancements of front end UI to support additional search capability for end user access | DS | Proposal
Enhancements to custom archiving / Data Mover and Scheduling software to support new media formats or build / recommend new software | DS | Proposal
Cut-over to Production environment | All | Proposal
Phased releases for multiple batches of media files migration | 3rd Party / DI | Proposal

## AWS Public Cloud Option
Activities | Owner | Phase
Infrastructure Setup
Identification of a Nearest region / AWS Local zone for Solution through AWS Speed test | DI | Proposal
Estimate the network connectivity required between Disney Data Center and AWS Cloud | DI | Proposal
Establish required connectivity between Disney Data Center and AWS Partner | DI | Execution
Identification of compatible Virtual gateways for reading and understanding the data from the Existing TS3500 and TS1150 | DI | Proposal
Design pattern for Different Media types and Budled approach media management | DI | Proposal
Storage sizing and Life cycle policy management in AWS using LCP , Storage Lens | DI | Proposal
Sizing of server / storage required to host the solution during migration process | DI
Sizing of server / storage required to integrate the MAM and Archival Solution | DI | Proposal
Sizing of server / storage required to implement DR / Business Continuity and Asset Preservation solutions | DI | Proposal
Sizing of custom archiving, data mover and MAM software in the Data Center and associated integration | DI | Proposal
Acquisition and provisioning of required hardware gear in Data Center | DI | Execution
Perform feasibility checks using AWS services namely AWS Snowball and Tape Gateway | DI | Execution
For faster retrieval globally, test possibility of data localization using tools such as AWS Local Zones, Cache for different types of data | DI | Proposal
Compare latency of AWS solution with the existing Disney's Tape based solution | DI | Execution
Calculate egress and ingress cost for Disney's Data Requirements | DI | Proposal
Identify feasibility of AWS IAM or any other service for access governance | DI | Proposal
Creating a DR env in AWS | DI | Proposal
Professional Services
Identification of a 3rd party to support implementation of data conversion / extraction | 3rd Party / DI | Proposal
Installation and configuration of content management system / alterantes to current MAM model | DS | Execution
Implementation of metadata workflows of existing media assets in AWS | 3rd Party / DI | Proposal
Extraction of Data from tape libraries using custom archiving software | 3rd Party/DI | Proposal
Conversion of existing legacy media file formats to newer formats with metadata enrichment | 3rd Party / DI | Proposal
Migration of files to AWS Cloud Storage (test environment) | DS | Proposal
Enrichment of MAM Media Catalogue with additional metadata elements & location of the media asset (during migration) | DS | Proposal
Enhancements of MAM API to support co-existence of media files on-prem & support additional search criterion | DS | Proposal
Enhancements of front end UI to support additional search capability for end user access | DS | Proposal
Enhancements to custom archiving / Data Mover and Scheduling software to support new media formats or build / recommend new software | DS | Proposal
Cut-over to Production environment | DS | Proposal
Phased releases for multiple batches of media files migration | DS | Proposal
If needed, Identify the appropriate backup software (VeeAM, Dell EMC, etc.) which can work with AWS according to Disney's requirements | DS | Proposal
Check for Data Integrity related checks using services either provided by AWS or third-party | DS | Execution
Identify the sequence of movement of data to Cloud (Metadata file, followed by genres of media etc.) | DS | Proposal